## Schedule
[23 empty] | Plan | – –>
Project Management |  |  |  | Today = |  |  |  |  | #N/A | [13 empty] | Actual | ––>
Sl No. | Activity | Start | End | December | [22 empty] | January | [30 empty] | February | [28 empty] | March
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16
|  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114
1 | Discussion with Machine Vendors | 2 | 29 | bar: Week 1 10 2 to Week 5 6 29
|  | 3 | 30 | Week 1 11 3: –––––; Week 1 12 4: –––––; Week 1 13 5: –––––; Week 1 14 6: –––––; Week 1 15 7: –––––; Week 2 16 8: –––––; Week 2 17 9: –––––; Week 2 18 10: –––––; Week 2 19 11: –––––; Week 2 20 12: –––––; Week 2 21 13: –––––; Week 2 22 14: –––––; Week 3 23 15: –––––; Week 3 24 16: –––––; Week 3 25 17: –––––; Week 3 26 18: –––––; Week 3 27 19: –––––; Week 3 28 20: –––––; Week 3 29 21: –––––; Week 4 30 22: –––––; Week 4 31 23: –––––; Week 4 1 24: –––––; Week 4 2 25: –––––; Week 4 3 26: –––––; Week 4 4 27: –––––; Week 4 5 28: –––––; Week 5 6 29: –––––; Week 5 7 30: ->
2 | Finalise the Machines and place order | 29 | 53 | bar: Week 5 6 29 to Week 8 30 53
3 | Selectin of Factory location | 29 | 50 | bar: Week 5 6 29 to Week 8 27 50
4 | Discussion for Funding | 38 | 45 | bar: Week 6 15 38 to Week 7 22 45
|  | 35 | 40 | Week 5 12 35: –––––; Week 6 13 36: –––––; Week 6 14 37: –––––; Week 6 15 38: –––––; Week 6 16 39: –––––; Week 6 17 40: ->
5 | Discuss with bank for loan | 40 | 54 | bar: Week 6 17 40 to Week 8 31 54
6 | Payment to Factory advance | 38 | 45 | bar: Week 6 15 38 to Week 7 22 45
7 | Payment to Machine Suppliers | 50 | 55 | bar: Week 8 27 50 to Week 8 1 55
8 | Apply to bank for subsidy | 50 | 55 | bar: Week 8 27 50 to Week 8 1 55
9 | Installation of Machinery | 60 | 75 | bar: Week 9 6 60 to Week 11 20 75
10 | Legal Registrations | 60 | 83 | bar: Week 9 6 60 to Week 12 28 83
|  | 45 | 67 | Week 7 22 45: –––––; Week 7 23 46: –––––; Week 7 24 47: –––––; Week 7 25 48: –––––; Week 7 26 49: –––––; Week 8 27 50: –––––; Week 8 28 51: –––––; Week 8 29 52: –––––; Week 8 30 53: –––––; Week 8 31 54: –––––; Week 8 1 55: –––––; Week 8 2 56: –––––; Week 9 3 57: –––––; Week 9 4 58: –––––; Week 9 5 59: –––––; Week 9 6 60: –––––; Week 9 7 61: –––––; Week 9 8 62: –––––; Week 9 8 63: –––––; Week 10 9 64: –––––; Week 10 10 65: –––––; Week 10 11 66: –––––; Week 10 12 67: ->
 | time axis 2013-12-09 to 2014-04-01
 | time axis 2013-12-09 to 2014-04-01
4.5
Excelhub
www.excelhub.org
Payroll software in excel – Free Software
PAN application form in excel with Database facility.
Income tax refund status, Assessment status, Assessee Profile Management in Excel
More excel Utilities